## Sheet1
Task | Estimated Time Cost (Hours) | Actual Time Cost (Hours) | 296 | 313
Requirements Analysis | 44 | 30 | 12580 | 13302.5
Feasibility Analysis | 7 | 5
Scalability Analysis | 3 | 1
Identify Key Users | 2 | 1
Identify the technology required | 7 | 4
Project schedule/cost estimation | 5 | 3
Aims and deliverables | 6 | 5
Ethical and legal issues | 5 | 5
SWOT analysis | 4 | 2
Risk assessment | 5 | 4
Database Management | 32 | 26
Use case diagram | 5 | 6
Top down ERD | 5 | 6
Bottom up ERD | 5 | 3
Merged ERD | 16 | 8
Create MySQL Database | 1 | 3
Login and accounts | 13 | 22
User sessions | 3 | 1
Different types of accounts (admin/baker/shopper) | 1 | 4
Reset password enabled | 1 | 4
Can log in to change their details, track and cancel their orders | 2 | 5
Shopper also should have the option for delivery or local pickup | 1 | 2
Edit Profile Details | 2 | 2
Make a ‘guest’ account | 2 | 2
Seller's Basic profile number of pictures limitation | 1 | 2
Enquiry form | 21 | 10
Captcha implementation | 5 | 2
Simple and easy to complete | 10 | 5
Encryption | 5 | 2
Input masks | 1 | 1
Discussion system | 28 | 30
Payment link implementation | 9 | 3
One to one discussion between baker and customer | 10 | 15
Discussion history | 7 | 10
Baker's information visible after enquiry | 2 | 2
Mapping | 5 | 10
WEB google maps API, simple lambda implementation in blank website | 1 | 1
Allows one location (customer) and outputs a list of bakers ‘available’ | 1 | 4
Allow more complex narrowing – SQL statement on goods/distance etc | 3 | 5
Ratings and reviews | 10 | 13
To rate a product, an approved purchase is required | 6 | 3
flag inappropriate reviews/pictures for review by admin | 2 | 5
Baker reviews by customers | 2 | 5
Payment system | 15 | 25
JSON API reference word pay | 5 | 15
Secure implementation | 10 | 10
Email notification | 14 | 14
Notification on website AND/or email | 2 | 2
A new event will send a notification | 3 | 2
Baker notification | 3 | 2
Customer notification | 3 | 3
Reset password | 3 | 5
File downloads | 5 | 9
pdf download of transactions | 3 | 3
Upload pictures of cakes to database | 2 | 6
Admin permissions | 13 | 25
Can alter/delete/create/view certain content | 3 | 5
Will have a list of waiting for approval submissions | 3 | 5
Can grant additional space for pictures | 2 | 3
Track any payments throughout the website | 3 | 8
Bill the sellers or retrieve information for billing purposes | 2 | 4
Hacking and bot proof | 13 | 16
Captcha | 4 | 2
SQL injection proofing | 4 | 3
Remove error messages from display | 1 | 2
Server side/form validation | 1 | 3
Password requirements (input masks) | 1 | 1
File uploads | 2 | 5
Testing and debuging | 93 | 102
Insert dummy data | 2 | 1
Join all different parts of the website together | 10 | 15
Create dummy accounts | 1 | 1
Test functionality | 80 | 85